## Cost - OLD
Rodgers Kitchen Project
High Level Cost Estimating
ReNew Labor Costs: |  |  | ReNew Material and Equipment:
Design/Permit Running | 7500 |  | Printing | 500
Structural Engineer (subcontracted) | 2000 |  | Lights and outlets | 2000
Project Management | included |  | Pipes and fittings | 500
Demo crew | 3000 |  | Framing materials/drywall/trims | 2000
Electrician | 4000 | Reference | Screws, nails, adhesives | 2000
Plumber | 4000 |  | Setting materials/grout | 1000
Framing/Drywall/Trims | 5000 |  | Total: | 8000
Flooring | 4000 | Reference
Cabinet/countertop installation | 6500 |  | Contingency 10%: | 5000
Tile installation | 3000
Painters | 3000
Total: | 42000 |  | Estimated Permit costs | 3000
Owner Provided:
Flooring materials | 500
Tile | 500
Appliances: | 7500
Countertops: | 1500
Cabinets: | 15000
Total: | 25000 |  | All-in Project Cost Estimate: | 78000

## WSB & Budget
Project Name: Kitchen Remodel, 123 Main St., Denver, CO
Project Team: |  | Team 1
Revision: |  | 0 / January 19, 2023
|  |  | Resource Name | Cost (USD) | Time Duration (Days)
1 | Initiation, Design & Documents
| 1.1 | Funding for Project | Owner | 300 | 10
| 1.2 | Design Development | ReNew | 8000 | 10
| 1.3 | Drawings/Coordination with engineer | ReNew | 1600 | 20
| 1.4 | Vendor and Sub-Contractor Contracts | ReNew | 1000 | 20
2 | Permits & Inspections
| 2.1 | Permits | ReNew | 3900 | 35
3 | Owner Procurement
| 3.1 | Owner orders materials and appliances | Owner | 9000 | 30
| 3.2 | Owner vendor measures and orders cabinets | Owner | 15000 | 25
| 3.3 | Owner selects and orders countertops | Owner | 1700 | 5
4 | Demolition
| 4.1 | Demolition | ReNew | 3000 | 5
5 | Construction
| 5.1 | Framing | ReNew | 4000 | 5
| 5.2 | Rough Electrical and Plumbing | ReNew | 7500 | 10
| 5.3 | Drywall | ReNew | 4000 | 5
| 5.4 | Install flooring | ReNew | 3700 | 5
| 5.5 | Install Cabinets | ReNew | 5000 | 7
| 5.6 | Install Countertops | ReNew | 1500 | 2
| 5.7 | Backsplash tile | ReNew | 2800 | 3
| 5.8 | Finished Electrical and Plumbing | ReNew | 3000 | 5
6 | Finishing Touches
| 6.1 | Trims | ReNew | 1200 | 2
| 6.2 | Paint | ReNew | 3000 | 5
| 6.3 | Final Inspections | ReNew | 500 | 3
Total Tasks |  |  |  | 79700
Contingency (10% of Total) |  |  |  | 7970
Total Project |  |  |  | 87670
Estimation Notes:
Full time people estimated as 8 hour workday.
1.1 | Assumes 6 hours of owner time (2 people) @ $25/hr to meet with banks and obtain HELOC.
1.2 | Architect cost is a flat fee but assumes 75 hours at $100/hr. throughout the duration of the project + $500 printing/reimbursables.
1.3 | Structural engineer is a flat fee (subcontracted to Architect) but assumes 16 hours at $100/hr. throughout the duration of the project.
1.4 | 1 part-time person $50/hr to coordinate subcontractor contracts.
2.1 | 1 part-time person 12 hrs. @$75/hr to submit plans and follow up with jurisdiction + $3,000 permit fees.
3.1 | 8 hours of Owner time @$25/hr. + 1 part-time person 3 hrs @$100/hr + $8,500 cost of materials and appliances
3.2 | Cost of Owner's Cabinet Vendor - includes all labor, materials and shipping costs. Excludes installation.
3.3 | 4 hours of Owner time @$25/hr. + 1 part-time person 1 hr @$100/hr + $1,500 cost of materials
4.1 | 2 full-time people @$25/hour + 1 part-time person supervising 4 hours @100/hr. + $600 removal & disposal costs
5.2 | 2 full-time people @$25/hour + 1 part-time person supervising 4 hours @100/hr. + $3,100 materials
5.3 | 2 full-time people @$25/hour + 1 part-time person supervising 4 hours @100/hr. + $1,600 materials
5.4 | 1 full-time person @$50/hour + 1 full time person assisting @$25/hr + 1 part-time person supervising 4 hours @100/hr. + $300 fasteners/adhesives. Floor materials provided by owner (included above).
5.5 | 1 full-time person @$50/hour + 1 full time person assisting @$25/hr + 1 part-time person supervising 4 hours @100/hr. + $400 fasteners/adhesives. Cabinets provided by owner (included above).
5.6 | 1 full-time person @$50/hour + 1 full time person assisting @$25/hr + $300 fasteners/adhesives. Countertop provided by owner (included above).
5.7 | 1 full-time person @$50/hour + 1 full time person assisting @$25/hr + 1 part-time person supervising 4 hours @100/hr. + $600 setting materials/grout. Tile provided by owner (included above).
5.8 | 2 full-time people @$25/hour + 1 part-time person supervising 4 hours @100/hr. + $600 materials
6.1 | 2 full-time people @$25/hour + 1 part-time person supervising 2 hours @100/hr. + $200 materials
6.2 | 2 full-time people @$25/hour + 1 part-time person supervising 4 hours @100/hr. + $600 materials
6.3 | 4 hrs of Owner time @$25/hr + 1 part-time person 4 hrs. @$75/hr to meet with inspectors and get final sign-offs.

## WBS Scratch Paper
WBS
Revision History
No. | Date | Description
001 | 2023-01-21 | Original release
[5 empty] | Resource Name | Cost (USD) | Time Duration (days) |  | Aaron (Owner) | Kerry (Lead PM) | Aimee (Designer) | James (Permitting) | Cicelyn (Budgets/Admin) | Joanne (Schedule Owner) | Structural Engineer | Cabinet Vendor | Countertop Vendor | Subcontractors
1 |  | Funding for Project |  |  | Owner |  |  |  | R/A | I | I | I | R | I | I
|  | Design Development | [6 empty] | A | R | R | I | C | I | C
|  | Drawings/Coordination with engineer | [6 empty] | C | R/A | R | I | I | I | R
|  | Permits | [6 empty] | I | I |  | R/A | I | I |  |  |  | I
|  | Vendor and Sub-Contractor Contracts | [6 empty] | I | A |  |  | R | R |  |  |  | R
|  | Owner orders materials and appliances | [6 empty] | R/A | I | C |  | I | I |  |  |  | I
|  | Demolition* | [6 empty] | A | R | C |  | I | I | C |  |  | R
|  | Framing | [6 empty] | A | R | C |  | I | I | C |  |  | R
|  | Rough Electrical and Plumbing | [6 empty] | A | R | C |  | I | I |  |  |  | R
|  | Drywall | [6 empty] | A | R | C |  | I | I |  |  |  | R
|  | Install flooring | [6 empty] | A | R | C |  | I | I |  |  |  | R
|  | Owner vendor measures and orders cabinets | [6 empty] | R | I | C |  |  | I |  | R |  | I
|  | Install Cabinets | [6 empty] | A | R | C |  | I | I |  |  |  | R
|  | Owner selects and orders countertops | [6 empty] | R | I | C |  |  | I |  |  | R | I
|  | Install Countertops | [6 empty] | A | R | C |  | I | I |  |  |  | R
|  | Backsplash tile | [6 empty] | A | R | C |  | I | I |  |  |  | R
|  | Finished Electrical and Plumbing | [6 empty] | A | R | C |  | I | I |  |  |  | R
|  | Trims and Paint | [6 empty] | A | R | C |  | I | I |  |  |  | R
|  | Final Inspections | [6 empty] | I | I | C | R/A | I | I | C |  |  | I
| Summary Tasks |  | Work Packages |  | Resource Name | Cost (USD) | Time Duration (Days)
| No. | Description | No. | Description |  |  |  | Notes
| 1 | Design & Documents
|  |  | 1.1 | Funding for Project | Owner | 300 | 10 | Assumes 6 hours of owner time (2 people) @ $25/hr to meet with banks and obtain HELOC.
|  |  | 1.2 | Design Development | ReNew | 8000 | 10 | Architect cost is a flat fee but assumes 75 hours at $100/hr. throughout the duration of the project + $500 printing/reimbursables.
|  |  | 1.3 | Drawings/Coordination with engineer | ReNew | 1600 | 20 | Structural engineer is a flat fee (subcontracted to Architect) but assumes 16 hours at $100/hr. throughout the duration of the project.
|  |  | 1.4 | Vendor and Sub-Contractor Contracts | ReNew | 1000 | 20 | 1 part-time person $50/hr to coordinate subcontractor contracts.
| 2 | Permits & Inspections
|  |  | 2.1 | Permits | ReNew | 3900 | 160 | 1 part-time person 12 hrs. @$75/hr to submit plans and follow up with jurisdiction + $3,000 permit fees.
| 3 | Procurement
|  |  | 3.1 | Owner orders materials and appliances | Owner | 9000 | 30 | 8 hours of Owner time @$25/hr. + 1 part-time person 3 hrs @$100/hr + $8,500 cost of materials and appliances
|  |  | 3.2 | Owner vendor measures and orders cabinets | Owner | 15000 | 25 | Cost of Owner's Cabinet Vendor - includes all labor, materials and shipping costs. Excludes installation.
|  |  | 3.3 | Owner selects and orders countertops | Owner | 1700 | 5 | 4 hours of Owner time @$25/hr. + 1 part-time person 1 hr @$100/hr + $1,500 cost of materials
| 4 | Demolition
|  |  | 4.1 | Demolition | ReNew | 3000 | 5 | 2 full-time people @$25/hour + 1 part-time person supervising 4 hours @100/hr. + $600 removal & disposal costs
| 5 | Construction
|  |  | 5.1 | Framing | ReNew | 4000 | 5 | 2 full-time people @$25/hour + 1 part-time person supervising 4 hours @100/hr. + $1,600 materials
|  |  | 5.2 | Rough Electrical and Plumbing | ReNew | 7500 | 10 | 2 full-time people @$25/hour + 1 part-time person supervising 4 hours @100/hr. + $3,100 materials
|  |  | 5.3 | Drywall | ReNew | 4000 | 5 | 2 full-time people @$25/hour + 1 part-time person supervising 4 hours @100/hr. + $1,600 materials
|  |  | 5.4 | Install flooring | ReNew | 3700 | 5 | 1 full-time person @$50/hour + 1 full time person assisting @$25/hr + 1 part-time person supervising 4 hours @100/hr. + $300 fasteners/adhesives. Floor materials provided by owner (included above).
|  |  | 5.5 | Install Cabinets | ReNew | 5000 | 7 | 1 full-time person @$50/hour + 1 full time person assisting @$25/hr + 1 part-time person supervising 4 hours @100/hr. + $400 fasteners/adhesives. Cabinets provided by owner (included above).
|  |  | 5.6 | Install Countertops | ReNew | 1500 | 2 | 1 full-time person @$50/hour + 1 full time person assisting @$25/hr + $300 fasteners/adhesives. Countertop provided by owner (included above).
|  |  | 5.7 | Backsplash tile | ReNew | 2800 | 3 | 1 full-time person @$50/hour + 1 full time person assisting @$25/hr + 1 part-time person supervising 4 hours @100/hr. + $600 setting materials/grout. Tile provided by owner (included above).
|  |  | 5.8 | Finished Electrical and Plumbing | ReNew | 3000 | 5 | 2 full-time people @$25/hour + 1 part-time person supervising 4 hours @100/hr. + $600 materials
| 6 | Finishing Touches?
|  |  | 6.1 | Trims |  | 1200 | 2 | 2 full-time people @$25/hour + 1 part-time person supervising 2 hours @100/hr. + $200 materials
|  |  | 6.2 | Paint |  | 3000 | 5 | 2 full-time people @$25/hour + 1 part-time person supervising 4 hours @100/hr. + $600 materials
|  |  | 6.3 | Final Inspections |  | 500 | 3 | 4 hrs of Owner time @$25/hr + 1 part-time person 4 hrs. @$75/hr to meet with inspectors and get final sign-offs.
|  |  | 5.6 | Backsplash tile | ReNew | 2800 | 3 | 1 full-time person @$50/hour + 1 full time person assisting @$25/hr + 1 part-time person supervising 4 hours @100/hr. + $600 setting materials/grout. Tile provided by owner (included above).

## RACI
Rodgers Kitchen Project
RACI
R | Responsible (who does the work)
A | Approval (decision authority)
C | Consulted (consider their opinions)
I | Informed
Activity: | Task or Phase: | Aaron (Owner) | Kerry (Lead PM) | Aimee (Designer) | James (Permitting) | Cicelyn (Budgets/Admin) | Joanne (Schedule Owner) | Structural Engineer | Cabinet Vendor | Countertop Vendor | Subcontractors
A | Funding for Project | R/A | I | I | I | R | I | I |  |  |  | Aaron / Cicelyn
B | Design Development | A | R | R | I | C | I | C |  |  |  | Kerry / Aimee
C | Drawings/Coordination with engineer | C | R/A | R | I | I | I | R |  |  |  | Kerry / Aimee / Structural Engineer
D | Permits | I | I |  | R/A | I | I |  |  |  | I | James
E | Vendor and Sub-Contractor Contracts | I | A |  |  | R | R |  |  |  | R | Cicelyn / Joanne / Subcontractors
F | Owner orders materials and appliances | R/A | I | C |  | I | I |  |  |  | I | Aaron / Cicelyn / Joanne
G | Demolition* | A | R | C |  | I | I | C |  |  | R | Kerry / Subcontractors
H | Framing | A | R | C |  | I | I | C |  |  | R | Kerry / Subcontractors
I | Rough Electrical and Plumbing | A | R | C |  | I | I |  |  |  | R | Kerry / Subcontractors
J | Drywall | A | R | C |  | I | I |  |  |  | R | Kerry / Subcontractors
K | Install flooring | A | R | C |  | I | I |  |  |  | R | Kerry / Subcontractors
L | Owner vendor measures and orders cabinets | R | I | C |  |  | I |  | R |  | I | Aaron / Cabinet Vendor
M | Install Cabinets | A | R | C |  | I | I |  |  |  | R | Kerry / Subcontractors
N | Owner selects and orders countertops | R | I | C |  |  | I |  |  | R | I | Aaron / Countertop Vendor
O | Install Countertops | A | R | C |  | I | I |  |  |  | R | Kerry / Subcontractors
P | Backsplash tile | A | R | C |  | I | I |  |  |  | R | Kerry / Subcontractors
Q | Finished Electrical and Plumbing | A | R | C |  | I | I |  |  |  | R | Kerry / Subcontractors
R | Trims and Paint | A | R | C |  | I | I |  |  |  | R | Kerry / Subcontractors
S | Final Inspections | I | I | C | R/A | I | I | C |  |  | I | James

## Risk Analysis
Rodgers Kitchen Project
Risk Analysis
Probability Rating (P) |  |  |  | Risk Level (PxS)
A | Extremely Unlikely |  |  |  | I | II | III | IV | V
B | Remote |  |  | A | Low | Low | Low | Low | Moderate
C | Occassional |  |  | B | Low | Low | Low | Moderate | High
D | Reasonably Possible |  |  | C | Low | Low | Moderate | High | Unacceptable
E | Frequent |  |  | D | Low | Moderate | Moderate | High | Unacceptable
|  |  |  | E | Moderate | Moderate | High | Unacceptable | Unacceptable
Severity Rating (S)
I | Very Minor
II | Minor
III | Moderate
IV | Critical
V | Catastrophic
Risk ID Number | Risk | Probability (P) | Severity (S) | Risk Level | Remediation
1 | Appliances on back order | D | III | M
2 | Ordered wrong item - color or style is wrong | C | III | M
3 | Did not order extra flooring- cut too many edges | C | III | M
4 | Chosen appliance doesn't fit through door | B | III | L
5 | Can't find workers | D | II | M
6 | Paint spills & splashes on everything | B | IV | M
7 | Windows / tiles break | C | III | M
8 | Client chooses to change cabinets or sink or counter last minute. | B | III | L
9 | Appliances not fitting between shelves/cabinets | B | IV | U | Measure beforehand ; Find new cabinets or find new appliances
10 | Lighting fixture breaks / chandelier breaks | B | IV | M
11 | Contractors did horrible job - fired them & redo job | B | III | L
12 | Find termite droppings | B | IV | M
13 | Found mold | C | IV | H
14 | Foundational issues | C | IV | H
15 | Too many plugs on a breaker? | D | II | M
16 | Rotting wood around kitchen (window?) / mold in wall | C | IV | H
17 | Water pipe burst / Pipe rusted | B | IV | M
18 | Building not up to code | C | III | M
19 | Gas leak | B | IV | M
20 | Faulty Electrical | C | III | M
21 | Flooding/Blizzard/Hurricane | A | V | U | Schedule project during spring time
22 | Power Outage | B | IV | M
23 | Load limit for flooring | B | I | L
24 | Asbestos | C | IV | H
25 | Kitchen floods | B | III | L
26 | Don't get permit approved on time | D | IV | M
27 | Roof breaks/leaks | C | V | U | Find roof contractor / permits / prevent mold/ fix ceiling
28 | Subflooring uneven | C | II | L
29 | Electrical Fire? | B | IV | U | Not mixing chemicals together ; hire licensed electricians; have fire extinguisher in case
30
31
32
33
34

## Precedence Table w Time Estimat
Project Name: Kitchen Remodel, 123 Main St., Denver, CO
Project Team: | Team 1
Revision: | 0 / January 19, 2023
Days
Task ID | Task Description | Immediate Predecessor(s) | Optimistic | Most Likely | Pessimistic | Expected Time
1.1 | Funding for Project | - | 3 | 10 | 30 | 12.1667
1.2 | Design Development | 1.1 | 10 | 10 | 25 | 12.5
1.3 | Drawings/Coordination with engineer | 1.2 | 12 | 20 | 26 | 19.6667
1.4 | Vendor and Sub-Contractor Contracts | 1.3 | 3 | 20 | 22 | 17.5
2.1 | Permits | 1.3 | 5 | 35 | 120 | 44.1667
3.1 | Owner orders materials and appliances | 1.3 | 15 | 30 | 45 | 30
3.2 | Owner vendor measures and orders cabinets | 5.3 | 20 | 25 | 30 | 25
3.3 | Owner selects and orders countertops | 5.5 | 4 | 5 | 6 | 5
4.1 | Demolition | 1.4,2.1 | 4 | 5 | 5 | 4.8333
5.1 | Framing | 4.1 | 3 | 5 | 6 | 4.8333
5.2 | Rough Electrical and Plumbing | 5.1 | 8 | 10 | 13 | 10.1667
5.3 | Drywall | 5.2 | 1 | 5 | 6 | 4.5
5.4 | Install flooring | 3.1,5.3 | 2 | 5 | 5 | 4.5
5.5 | Install Cabinets | 3.2,5.4 | 4 | 7 | 8 | 6.6667
5.6 | Install Countertops | 3.3 | 2 | 2 | 3 | 2.1667
5.7 | Backsplash tile | 5.6 | 2 | 3 | 4 | 3
5.8 | Finished Electrical and Plumbing | 5.7 | 2 | 5 | 5 | 4.5
6.1 | Trims | 5.7 | 1 | 2 | 2 | 1.8333
6.2 | Paint | 6.1 | 1 | 5 | 7 | 4.6667
6.3 | Final Inspections | 5.8 | 1 | 3 | 5 | 3
| Project End | 6.2,6.3 | 103 | 212 | 373 | 220.6667